## Gantt Chart
NYC Taxi Fare Prediction — Project Gantt Chart (Spring 2026)
Phase | Task / Milestone | W1 Jan 19 | W2 Jan 26 | W3 Feb 02 | W4 Feb 09 | W5 Feb 16 | W6 Feb 23 | W7 Mar 02 | W8 Mar 09 | W9 Mar 16 | W10 Mar 23 | W11 Mar 30 | W12 Apr 06 | W13 Apr 13 | W14 Apr 20 | W15 Apr 27 | W16 May 04
Phase 1 | Select project topic & dataset | ▶
Phase 1 | Download Jan 2024 Yellow Taxi file | ▶ | ◀
Phase 1 | Inspect January 2024 sample (notebook) |  | ▶ | ◀
Phase 1 | Document idea, objective, dataset |  |  | ▶ | ◀
Phase 2 | Write project planning documents |  |  |  | ▶ | ◀
Phase 2 | Design Big Data architecture |  |  |  |  | ▶ | ◀
Phase 2 | Define data lifecycle |  |  |  |  | ▶ | ◀
Phase 2 | Write paper Part 1 (Intro & Methodology) | [5 empty] | ▶ | ◀
Phase 3 | Download full 2024 monthly Parquet files | [6 empty] | ▶
Phase 3 | Spark processing & schema validation | [6 empty] | ▶ |  | ◀
Phase 3 | Data preprocessing & feature engineering | [8 empty] | ▶ |  | ◀
Phase 3 | EDA, SparkSQL & Window Functions | [10 empty] | ▶ | ◀
Phase 3 | Build ML Pipeline (LinearRegression) | [11 empty] | ▶ | ◀
Phase 3 | Model evaluation & save results | [12 empty] | ▶
Phase 3 | Community contribution document | [12 empty] | ▶ | ◀
Final | Write paper Part 2 (Results & Discussion) | [13 empty] | ▶ | ◀
Final | Technical documentation & README | [13 empty] | ▶ | ◀
Final | Final discussion / presentation prep | [14 empty] | ▶ | ◀

## Legend
Legend
Phase 1 — Dataset Introduction | Weeks 1–4: Jan 19 – Feb 15 2026
Phase 2 — Planning & Design | Weeks 4–7: Feb 9 – Mar 8 2026
Phase 3 — Preprocessing & Methodology | Weeks 7–14: Mar 2 – Apr 26 2026
Final — Paper & Presentation | Weeks 14–16: Apr 20 – May 3 2026